## Slide 1
Notes: Hoofdslide

## Slide 2
Project management
TM Ghent 12/2/20
Notes: Tussentitel versie 1 / niveau 1

## Slide 3
Getting ready for phase 2
Notes: Tussentitel versie 2 / niveau 2

## Slide 4: Timeline
    Phase 2 Application:
      Feedback on draft proposal by all PPs: 20/2
      Deadline for signed Letters of Commitment: 20/2
      Submission application form: 2/3
      Start phase 2: 14/5
        When approved: period between 2/3 – 14/5 is eligible as well

## Slide 5: Letter of Commitment (LoC)
    Fixed template on Basecamp
    Signed by elected representative
      Any PP without elected representative?
    Scanned LoCs are compulsory part of the application
      If 1 is missing, our appliciation is NOT eligible
    Get 2 copies signed: 1 for you, 1 for LP
      Scan to LP by 20/2
      Original to LP by 25/2 (see Basecamp for address)
      Round of the group

## Slide 6: Roles in phase 2
    Project coordinator (involved in transnational level)
    ULG coordinator (local level)
    Finance Officer
    Communication Officer
      some roles can be combined
      URBACT Guidelines: 1 full-time
      Project coordinator: good knowledge of English!

## Slide 7
Budget phase 2
Notes: Tussentitel versie 2 / niveau 2

## Slide 8: General principles
    Budget Phase 1 + Phase 2 = 750.000€ max
      Budget phase 1: 149.818€
      Unspent budget from phase 1 > phase 2
    PPs Less Developed regions:
      80% for staff and external expertise due to difference in salaries and costs
        Travel & Accommodation: 100%

## Slide 9: From proposal to final budget
    Step 1: decide on number and hosts TMs e.o.
      Budget for hosting TM: 4.000€
    Step 2: adapt the propsal to you local needs by 18/2
      Total budget per PP is fixed, you cannot exceed that
      Pay special attention to
        Staff (on the payroll of the official partner organisation) vs External staff (freelancers, cooperating agencies, hired external project coordinators,…)
        T&A: only for staff that is on the payroll of your organisation
          For ULG-members, external project coordinators,…: ExEx non-staff travel
        Costs for FLC

## Slide 10: Recap: budgetlines in URBACT
    See ppt on project management TM Naples for extended info
Budgetline | What? | Underlying evidence
STAFF | Staff on the payroll of the official PP Max. 35-40% of your budget can go to staff & external project coordination | Timesheets (unless full time on project – almost impossible with URBACT budget)
OFFICE & ADMIN | Overhead | None. Automatically 3% on staff
TRAVEL & ACCOMODATION | Costs for travel (plain, public transport, car) and hotel, meals, daily allowances and visa costs Unitcost of €650 per person per travel Only for staff of the official PP | Original boarding pass, trainticket, hotel invoice,… Agenda, meeting minutes, attendance list,..
EXTERNAL EXPERTISE | Expertise and services provided by a public/private body or a natural person outside of the partner organisation Costs paid on the basis of contracts, by invoice or reimbursement request | Public procurement: evidence of selection process Contracts mention clear link to ROOF/URBACT Outputs produced (study, video, translated doc,…), invoice

## Slide 11: How it will be visible in the application form

## Slide 12: Budget flexibility
    Minor changes
      20% flex between budgetlines
      No formal procedure – explain in the Progress Report
    Major changes
      Only once
        Prepared in the Mid Term TM
        Formal procedure nov 2021 – feb 2022
      For devitiations in the budget above 20%
        Between budget lines
        Between partners
      Argumented and approved by the Monitoring Comittee
      Formal reprogramming of the project

## Slide 13: Small Scale Actions (SSA)
    “A Small Scale Action is experimentation. It is an idea or a concept, perhaps already tried in another city, which can be tested to check the relevance, feasibility and added value of its implementation in different local contexts“
      Limited in time and scale
      The right to fail
      Test > measure > evaluate > (not) adopt in your IAP
      ! No infrastructure investments (never in URBACT)
      Max. 10.000€ per PP – up to you on which budget lines
      Completed by September 2021 > lessons included in first draft IAP
        Read more in the Guide to APNs p 17-19

## Slide 14
Claim 1
Notes: Tussentitel versie 2 / niveau 2

## Slide 15: Reporting rounds
    3 reporting rounds
      Phase 1: 1 claim
      Phase 2: 2 claims (yearly)
    Payment claim:
      Progress Report: reflecting the progress on partner and network level & deliverables
        Reporting per WP
          WP3: Local actions – main input from PPs
        LP asks input from ALL PPs
        Edited & submitted by LP in SYNERGIE
      Financial Reporting

## Slide 16: Synergie
    SYNERGIE: project management platform for claims, progress report,…
      https://synergie-cte.asp-public.fr/
      Everybody has access?
    Guidelines on Basecamp > Docs & Files > Phase 1 reporting – SYNERGIE Guidance Notes

## Slide 17: Financial reporting Phase 1
2/04/2020 | 8/04/2020 | 15/05/2020 | 28/05/2020 | 02/06/2020
Input Synergie of all costs | All cost are validated | Collecting all signed certificates | FLC LP grouped claim | Deadline claim to URBACT
Lead partners & Project partners | LP and PP | PP and LP | LP | LP

## Slide 18
Input expenditures Synergie
Deadline: 02/04/2020
Input ALL expenditures in Synergie
Costs made Phase 1 period:
    2nd September till 2nd March
Corresponding budgetlines without exceeding maximum amount
Flexibility 20% between budgetlines and between partners

## Slide 19
Input expenditures Synergie

## Slide 20
Input expenditures Synergie
Comment should justify the amount and link to project
WHY WHEN WHO WHAT
Ex: travel cost => train ticket – Patricia V – Paris – Ghent – 11/09/2019 – training URBACT

## Slide 21
LP validates expenditures
    Deadline: 08/04/2020
    LP checks if everything is correct
      Workpackage wrong
      details incomplete
      Cost wrong budgetcategory
    If there are still mistakes =>
      PP corrects and validates again
    Expenditures correct
      LP validates
      Cost are available for FLC now

## Slide 22
PP sends signed certificates LP
    Deadline: 15/05/2020
    FLC can check and certify
    Set a date with your FLC so you will be on time!
    After approval FLC you can download the certificate in Synergie
    FLC signs the certificate
    PP sends by email to sana.liou@stad.gent
    LP collects all signed certificates by 15/05/2020

## Slide 23
FLC LP signs grouped claim
    Deadline: 28/05/2020
After receiving all signed certificates from PP
LP FLC delivers grouped claim certificate
Financial part of the progress report can only be completed after all PP claims are certified in SYNERGIE

## Slide 24
LP sends to URBACT
    Deadline: 02/06/2020
Documents to be submitted by LP
    Certificate of expenditure per partner signed by FLC
    Payment Claim grouping all certificates by LP
    Progress Report by LP with input from partners

## Slide 25
Appointment FLC SYNERGIE
Check your system in the URBACT Guide to Network Management > Annex 4 (p. 28-32)
    Centralised system = State FLC
      Costs mostly borne by Member State
      Get in touch on national rules and timeframe
      Romania, Greece, Poland, Belgium Wallonia
    Decentralised system = you appoint your FLC yourself AND gets approved by Approbation Body
      public procurement rules in case you chose external controller!)
      FLC needs to fill in a questionnaire checklist with details, skills,…
    Word-version on Basecamp – final version need to be filled in online
    Check Annex 4 for contact details Approbation Body
  Costs borne by PPs budget
  UK, Denmark, France, Belgium Flanders, Portugal

## Slide 26
Appointment FLC SYNERGIE

## Slide 27
Appointment FLC SYNERGIE

## Slide 28
Appointment FLC SYNERGIE
Select correct FLC in list or make new one in Synergie
Fill in checklist in SYNERGIE
Email your national contact point validate your FLC in SYNERGIE!
See link list contact person
FLC will not be able to validate costs in Synergie if not validated

## Slide 29
Guidelines Synergie
Basecamp: APN ROOF > Docs & Files > Phase 1 Reporting – SYNERGIE GUIDANCE NOTES
    Be sure to check following guidance notes:
    Guidance Note1: Getting the FLC approved
    Guidance Note 3: Accounting Expenditure
    Guidance Note 7: Entering ERDF & Exports

## Slide 30: Support on project management
    Ghent team:
    Ariana.Tabaku@stad.gent
      General project management & contractuel documents
      Contact point URBACT secretariat
    Sana.Liou@stad.gent
      Financial reporting & Synergie
URBACT III Programme Manual: please read carefully
    Factsheet 2A Action Planning Networks
    Factsheet 2E Network Management
    Factsheet 2F Financial Management & Control
    Sessions in transnational meetings
    If needed, telco or Skype sessions